## Sheet1
Activity/Milestone | Start Date | End Date | Duration
Meet QR Management to discuss potential scope | 2019-09-01 | 2019-09-06 | 5
Identify potential project opportunities | 2019-09-01 | 2019-09-06 | 5
Refine scope | 2019-09-09 | 2019-09-13 | 4
Arrange meetings with line management | 2019-09-09 | 2019-09-13 | 4
Meet with Engineers to review current process | 2019-09-11 | 2019-09-13 | 2
Obtain initial datasets | 2019-09-16 | 2019-09-20 | 4
Complete initial heatmaps | 2019-09-20 | 2019-09-27 | 7
Identify opportunities for machine learning | 2019-09-21 | 2019-09-27 | 6
Identify additional parameters required | 2019-09-22 | 2019-09-27 | 5
Communication/request for additional information | 2019-09-30 | 2019-10-03 | 3
Finalise workplan and initial approach | 2019-10-04 | 2019-10-06 | 2
Pursue additional information requested | 2019-10-07 | 2019-10-11 | 4
Project Proposal submitted | 2019-10-03 | 2019-10-11 | 8
Proposal Presentation Slides and Video | 2019-10-03 | 2019-10-11 | 8
Finalise parameters to be used within the model | 2019-10-04 | 2019-10-18 | 14
Complete initial model | 2019-10-04 | 2019-11-15 | 42
Objective tests of predictive power | 2019-10-25 | 2019-11-01 | 7
Develop visualisation | 2019-10-25 | 2019-11-15 | 21
Submit Progress Report | 2019-11-07 | 2019-11-08 | 1
Complete visualisation | 2019-11-14 | 2019-11-21 | 7
Conduct end-user-testing | 2019-11-21 | 2019-11-22 | 1
Refine user-interactivity model | 2019-11-23 | 2019-11-25 | 2
Submit Poster Presentation Video | 2019-11-28 | 2019-11-29 | 1
Submit Final Report | 2019-11-28 | 2019-11-29 | 1